FRESH DIGITAL — DIGITAL GROWTH STRATEGY PROPOSAL
U.S. POLO ASSN. THAILAND

Integrated Social Media & E-Commerce Growth Strategy Proposal (2-Phase Roadmap)

1. Executive Summary

Fresh Digital is pleased to submit this comprehensive digital marketing growth proposal for U.S. Polo Assn. Thailand. As the official brand of the United States Polo Association (USPA), U.S. Polo Assn. carries an unmatched heritage of authentic sport, timeless American style, and accessible luxury sportswear.

This proposal establishes a strategic 2-phase roadmap designed to maximize return on ad spend (ROAS) across social media and search channels while transitioning the brand into a high-performing e-commerce powerhouse upon the launch of its new Shopify store in October 2026.

📌 Commercial Summary & Strategic Parameters • Monthly Media Budget: THB 100,000 / month (100% allocated to ad platform spend) • Monthly Agency Management Fee: THB 35,000 / month (excluding 7% VAT) • Brand Hub & Social Signals: https://linktr.ee/uspoloassn.th (@uspoloassn.th, LINE OA @uspolo) • Phase 1 (Aug - Mid-Oct 2026): Social Media Marketing Engine (Facebook, Instagram, TikTok, LINE OA) • Phase 2 (Mid-Oct 2026+): Shopify Full-Funnel E-Commerce, CPAS (Marketplaces) & Google Shopping Ads

2. Brand Context & Market Positioning

U.S. Polo Assn. occupies a distinct sweet spot in Thailand's fashion landscape: authentic sport heritage, premium quality fabrications, and classic preppy aesthetics at an accessible price point compared to luxury legacy competitors.

Core Audience Profiles in Thailand

1. Classic Lifestyle & Smart Casual: Ages 25–42, working professionals, corporate executives, and smart-casual dressers seeking stylish, durable polo shirts and office-to-weekend apparel.

2. Golf & Sport Heritage Enthusiasts: Ages 20–35, sports enthusiasts, golf and polo fans, active lifestyle individuals who value authentic American sportswear heritage.

3. Gifting & Lifestyle Accessory Shoppers: Ages 22–38, seasonal shoppers purchasing premium branded apparel, caps, bags, and accessories as gifts for partners and family.

3. Phase 1 Strategy: Social Media Marketing Plan (August – Mid-October 2026)

During the site construction phase, 100% of media spend will be deployed across high-engagement social media platforms. The objective is to build brand awareness, capture active buyer intent, and convert prospects directly via Social Commerce, direct messaging (FB/IG DMs), LINE OA (@uspolo), and existing marketplace links.

Channel Roles & Campaign Architecture (Phase 1)

• Facebook & Instagram Ads (Meta): Prospecting & Visual Storytelling. Focus on high-performing video Reels, lifestyle image carousels, and collection ads highlighting fit, fabric, and iconic logo detailing. Drives traffic to Linktree & direct messages.

• TikTok Ads Platform: High-Energy Trend & Lifestyle Discovery. Deploy short-form 9:16 videos, creator Spark Ads, and outfit-of-the-day (OOTD) styling content targeting fashion-conscious Gen Z & Millennials.

• LINE Ads Platform (LAP): Direct High-Intent Conversion & CRM. Targeted LAP (LINE Ads Platform) campaigns to drive LINE OA (@uspolo) add-friends for direct chat sales, VIP membership registration, and catalog distribution.

Phase 1 Monthly Budget Allocation (THB 100,000 / Month)

| Channel | Monthly Budget (THB) | Share (%) | Primary Campaign Objectives | Target Output / Funnel Stage |
| --- | --- | --- | --- | --- |
| Meta Ads (FB & IG) | THB 50,000 | 50% | Reels Views, Engagement, Linktree Traffic, DMs | Top & Middle Funnel (Awareness & Intent) |
| TikTok Ads | THB 30,000 | 30% | Video Views, CTR, TikTok Profile & Link Clicks | Top Funnel Discovery & Gen Z Reach |
| LINE Ads (LAP) | THB 20,000 | 20% | LINE OA Friend Adds (@uspolo), Chat Conversions | Bottom Funnel Social Sales & CRM |
| Total Media Budget | THB 100,000 | 100% | Integrated Social Commerce Engine | Full Phase 1 Social Coverage |

4. Phase 2 Strategy: Full-Funnel E-Commerce Launch (Mid-October 2026 Onwards)

Upon completion of the new Shopify e-commerce website, media campaigns will immediately pivot toward direct website purchase optimization, dynamic remarketing, Marketplace CPAS, and Google Shopping Search capture.

Phase 2 Monthly Budget Re-Allocation (THB 100,000 / Month)

| Channel / Strategy | Monthly Budget (THB) | Share (%) | Campaign Focus & Technology | Expected KPI Focus |
| --- | --- | --- | --- | --- |
| Meta Web Conversions & ASC | THB 35,000 | 35% | Advantage+ Shopping, Web Purchase Pixel/CAPI, DPA | Direct Web ROAS & Purchase Volume |
| Google Shopping & Search / PMax | THB 30,000 | 30% | Google Merchant Center, PMax Retail, Exact Brand Search | High-Intent Capture & Web Revenue |
| CPAS (Shopee / Lazada) | THB 20,000 | 20% | Collaborative Dynamic Catalog Ads to Marketplace Stores | Marketplace ROAS & Volume Sales |
| TikTok Web Conversion | THB 15,000 | 15% | TikTok Web Pixel, Spark Ads to Shopify Product Pages | Direct Web Orders & Youth Conversions |
| Total Media Budget | THB 100,000 | 100% | Full-Funnel E-Commerce Growth Stack | Omnichannel Brand Growth |

5. Deep Dive: CPAS (Collaborative Performance Advertising Solution)

CPAS enables U.S. Polo Assn. Thailand to run co-branded Meta ads directly linked to its official Shopee and Lazada brand stores. Meta dynamic ads display real-time inventory, pricing, and personalized product recommendations to users based on their marketplace browsing behavior.

Strategic Benefits of CPAS

• High Conversion Rate: Leverages Shopee/Lazada's high trust, local payment methods, and established consumer purchasing habits in Thailand.

• Automated Dynamic Retargeting: Runs Meta Dynamic Product Ads (DPA) targeting users who viewed or added items to cart on Shopee/Lazada without purchasing.

• Full Purchase Attribution: Closed-loop conversion reporting inside Meta Business Manager showing exact sales revenue and CPAS ROAS.

CPAS Setup Requirements & Prerequisites

1. Partner Agreement: Request CPAS Shared Catalog access from Shopee / Lazada Brand Portal team.

2. Meta Business Manager Linkage: Accept catalog share in Meta Business Manager and assign access to Fresh Digital agency assets.

3. Marketplace Product Feed Hygiene: Ensure product SKUs, stock levels, high-res image assets, and THB pricing are perfectly synchronized daily.

6. Deep Dive: Google Shopping Ads & Performance Max Strategy

Google Shopping Ads present visual product listings (image, brand, product title, price) directly at the top of Google Search results when Thai consumers query high-intent keywords like 'เสื้อโปโล U.S. Polo', 'polo shirt men', or 'เสื้อโปโลแท้'.

Google Shopping Architecture

• Shopify GMC Integration: Connects Shopify directly to Google Merchant Center (GMC) via the official Shopify Google Channel app, enabling automatic real-time product feed sync.

• Performance Max (PMax) for Retail: Combines Google Shopping, Search, Display, YouTube, and Discovery into a single AI-driven campaign optimizing for target ROAS.

• Branded & Category Search Defenses: Complemented by tight Brand & Apparel Exact/Phrase Search campaigns to defend brand keywords and capture specific high-value apparel queries.

Google Shopping Setup Requirements & Prerequisites

1. Google Merchant Center (GMC): Set up GMC account, claim and verify Shopify domain (`uspoloassn.co.th` or approved domain).

2. Policy & Compliance Verification: Ensure compliance with Google Shopping policies (clear return policy, visible contact information, secure HTTPS checkout, transparent shipping fees).

3. Product Feed Optimization: Optimize product titles (e.g. 'U.S. Polo Assn. - เสื้อโปโลผู้ชาย รุ่น Classic Fit สีส้ม'), ensure high-quality white-background product images, assign barcode/GTIN identifiers.

4. Advanced Purchase Tracking: Deploy GTM with native Google Ads Purchase conversion tags and Enhanced Conversions for accurate revenue tracking.

7. Implementation Timeline & Technical Setup Roadmap

To ensure a flawless launch in August and seamless e-commerce transition in October, the following 90-day timeline will be executed:

| Timeline | Phase | Key Tasks & Technical Deliverables | Milestones & Sign-offs |
| --- | --- | --- | --- |
| Weeks 1-2 (Aug) | Phase 1 Onboarding | Audit existing Meta/TikTok/LINE accounts, setup Business Manager permissions, install base pixels, draft ad creatives. | Campaign Launch (Phase 1 Social) |
| Weeks 3-6 (Aug-Sept) | Phase 1 Optimization | A/B test creative formats (Reels vs Carousel), optimize LAP LINE OA add-friends, refine custom audience lists. | Bi-Weekly Performance Review |
| Weeks 7-8 (Sept) | Phase 2 Preparation | Set up Google Merchant Center, sync Shopify feed draft, request Shopee/Lazada CPAS catalog sharing, audit GTM & CAPI. | CPAS & GMC Readiness Sign-off |
| Weeks 9-10 (Mid-Oct) | Phase 2 Go-Live | Launch Shopify site, activate Meta Web Conversions, ASC campaigns, Google Shopping/PMax, and CPAS Marketplace ads. | Full E-Commerce Stack Activation |
| Weeks 11-12 (Nov+) | Phase 2 Scale | Optimize ROAS across Web and CPAS, scale winning PMax/ASC ad sets, run dynamic retargeting campaigns. | Monthly Growth Strategy Review |

8. KPI Forecast Scenarios (30-Day Monthly Benchmarks)

Below are directional forecast scenarios based on THB 100,000 monthly media spend under typical Thai fashion market benchmarks. These scenarios serve as planning indicators and will be validated with live data during the initial 30 days of execution.

Phase 1 Forecast: Social Media & Social Commerce (Monthly THB 100,000 Media Budget)

| Metric / KPI | Conservative Scenario | Base Target Scenario | Stretch Scenario |
| --- | --- | --- | --- |
| Total Ad Impressions | 1,800,000 | 2,400,000 | 3,000,000 |
| Estimated Reach (Unique Users) | 750,000 | 1,000,000 | 1,350,000 |
| Link Clicks & Profile Visits | 18,000 | 26,000 | 35,000 |
| Average CTR (%) | 1.00% | 1.15% | 1.40% |
| LINE OA New Friend Adds (@uspolo) | 1,200 | 1,800 | 2,500 |
| FB/IG Direct Message Inquiries | 450 | 700 | 1,000 |
| Est. Social Commerce Revenue (THB) | THB 250,000 | THB 400,000 | THB 600,000 |
| Est. Social Commerce ROAS | 2.5x | 4.0x | 6.0x |

Phase 2 Forecast: Shopify E-Commerce & CPAS Growth (Monthly THB 100,000 Media Budget)

| Metric / KPI | Conservative Scenario | Base Target Scenario | Stretch Scenario |
| --- | --- | --- | --- |
| Shopify & Marketplace Traffic (Sessions) | 22,000 | 32,000 | 42,000 |
| Average Web Conversion Rate (%) | 1.20% | 1.60% | 2.20% |
| Total Completed E-Commerce Orders | 264 | 512 | 924 |
| Assumed Average Order Value (AOV) | THB 1,800 | THB 2,000 | THB 2,200 |
| Total E-Commerce Revenue (THB) | THB 475,200 | THB 1,024,000 | THB 2,032,800 |
| Overall Blended E-Commerce ROAS | 4.75x | 10.24x | 20.33x |

9. Commercial Terms & Management Fee Structure

Fresh Digital operates with complete fee transparency. Media spend is paid directly by the client to advertising platforms (Meta, Google, TikTok, LINE), ensuring 100% account ownership.

| Fee Item | Monthly Amount (THB) | Tax / VAT Terms | Scope & Deliverables Covered |
| --- | --- | --- | --- |
| Media Ad Spend (Paid directly to platforms) | THB 100,000 / month | Exempt / Direct Client Billing | 100% platform ad credits across Meta, TikTok, LINE, Google |
| Agency Monthly Management Fee | THB 35,000 / month | Excludes 7% VAT (THB 2,450) | Full end-to-end strategy, setup, creative direction, daily optimization & reporting |
| Total Monthly Investment | THB 135,000 / month | Plus 7% VAT on Agency Fee | Complete Integrated Digital Growth Partnership |

Scope of Agency Management Services

1. Strategic Setup & Integration: Account architecture design, pixel/CAPI setup, Google Merchant Center feed integration, CPAS catalog configuration.

2. Daily Campaign Optimization: A/B testing of ad copy, visual assets, target audiences, bidding strategies, and channel budget reallocations.

3. Creative Direction & Asset Guidance: Ad copy creation, visual moodboards, creative briefing for short-form video Reel/TikTok concepts.

4. Reporting & Commercial Review: Transparent bi-weekly performance updates and monthly strategic review meetings with actionable commercial insights.